## Sheet1
Issue_ID | Issue Description | TC_ID | Expected Result | Detected by | Status(open,fixed,closed) | Notes
Spr1_Iss1 | Dashboard is getting displayed differently in Safari and IE browsers. It is disturbing the alignment in some pages. (like partial display of cover images) | TC_17_App_Compatibility | Application should be browser compatible | Naresh Pasupuleti | Open | Gaurab
Spr1_Iss2 | Dashboard is not getting displayed in mobile browsers | TC_17.2_App_Compatibility | Application should be mobile compatible | Naresh Pasupuleti | Open | Gaurab
Spr1_Iss3 | Newsletter signup is accepting numeric values or special charecters as first name and last name, It is not throwing any validation error | TC_12.2_Newsletter_SignUp_validation | All the input fields should be validated successfully | Naresh Pasupuleti | Open | Garima
Spr1_Iss4 | while creating manager application is accepting numeric values and special characters for first,middle and last name | TC_13_Create_Manager | Only characters should be accepted for names as input | Naresh Kuresham | Open | Garima
Spr1_Iss5 | Accepting spaces before the names while creating a manager low prior | TC_13.2_Create_Manager_validation | No spaces are allowed as inputs for names while creating a manager | Naresh Kuresham | Open | Garima
Spr1_Iss6 | Confirm field is not higlighted when left blank. instead password field is highlighted with error message "The password confirmation does not match" | TC_13.7_Create_Manager_validation | Correct fields should be highlighted in case of errors | Naresh Kuresham | Open | Garima
Spr1_Iss7 | The confirmation popup for update and delete is not working for manager update and delete. | TC_15.2_Update_Manager_validation | A update pop up box is displayed asking for confirmation | Ravi Kant Singhania | Open | Gaurab
Issue_ID | Comment Description and ideal solution | TC_ID |  | Detected by | Status(open,fixed,closed) | Notes
Spr1_Cmm1 | Once, the user has clicked the register button of borrower, the navigated registration page is not uniquely signifying that, it belongs to borrower. Changing the heading from 'Register' to 'Business owner registration' would be good | TC_1.1_User_Reg_Borrower |  | Naresh Pasupuleti |  | Vandhana
Spr1_Cmm1 | Once, the user has clicked the register button of investor, the navigated registration page not is uniquely signifying that, it belongs to investor. Changing the heading from 'Register' to 'Investor registration' would be good | TC_1.2_User_Reg_Investor |  | Naresh Pasupuleti |  | Vandhana
Spr1_Cmm1 | There is no underline or any other way to clear understand that the user is in investing page. As per mockup , only Investing button should be highlited when he is in investing page. | TC_6_Investing_Tab |  | Naresh Pasupuleti |  | Vandhana
Spr1_Cmm1 | There is no underline or any other way to clearly understand that the user is in business loans page. As per mockup, only business loans button should be highlited when he is in business loans. | TC_7_BusinessLoans_Tab |  | Naresh Pasupuleti |  | Vandhana
Spr1_Cmm1 | Compared to the other pages, left space is a bit more for business loans page. Need to correct this. | TC_7.1_BusinessLoans_Page |  | Samyuktha Subbammagari |  | Vandhana
Spr1_Cmm2 | There is no underline or any other way to clearly understand that the user is in how it works page. As per mockup, only how it works button should be highlited when he is in how it works. | TC_8_How_It_Works_Tab |  | Naresh Pasupuleti |  | Vandhana
Spr1_Cmm4 | There is no underline or any other way to clearly understand that the user is in About Us page. As per mockup, only About Us button should be highlited when he is in About Us page. | TC_9_AboutUs_Tab |  | Naresh Pasupuleti |  | Vandhana
Spr1_Cmm5 | 3. Good display as ""Newsletter"" instead of ""News Letter"" 4.“Submit” or “Signup” is appropriate instead of “save” button" | TC_9.1_AboutUs_Page |  | Naresh Pasupuleti |  | Vandhana
Spr1_Cmm6 | Displaying an error message like 'This response has already been processed' is ideal. | TC_19_app_double_form_submission |  | Naresh Pasupuleti
Spr1_cmm7 | Add a cancel button for update manager |  |  |  |  | Gaurab
Spr1_cmm8 | Home page should be changed.
Spr1_CMM8 | Business Owner page has no heading |  |  |  |  | Vandhana
Password validation 1 uc 1lc and 8 characters skip security questions